## Slide 1: Building the Future of Housing with the External Review
Von Stange, Ed.D.
Assistant Vice-President of Student Life and
Senior Director, University Housing & Dining
The University of Iowa
Iowa City, IA
von-stange@uiowa.edu
UMR-ACUHO Conference
St. Louis, MO
October 24-26, 2013

## Slide 2: Learning Outcomes
1:Participants will receive information on preparing documents to perform an external review
2:Participants will gain perspective of an external review from a reviewer lens.
3: Participants will gain some perspective of the review from an institutional lens.

## Slide 3: Today’s agenda
Introduction of presenter
Why do a review?
Developing the charge for the review
Preparing documentation for review
Developing timeline for review
Communication between school and reviewers
The site visit - host perspective
Lessons learned from the review
Respond to questions

## Slide 4: Why do an External Review? Excerpts Michael Daley, 1989

## Slide 5: Why do an External Review? Excerpts Michael Daley, 1989
Improve overall program quality
Improve specific functions within the program
Clarify departmental goals
Improve service delivery
Assist in short and long range strategic planning
Enhance visibility, viability and legitimacy - inside and outside the department
Aid in staff development and training
Reinforce staff achievements; improve morale
Information for governing boards/accreditation
Leadership change

## Slide 6: Why did we review at Iowa?
Moving into a time of great change
  Unified dining operation
  New housing construction
  Potential replacement of family housing
Five years since last review
Expansion of Living-Learning Communities
Expansion of technology in the department

## Slide 7: Preparing for the Review – institutional perspective
Development of steering committee
Budget
Use of ACUHO-I Standards
Self assessment
Respond to potential staff apprehension
Identify and schedule individuals to review
Involve university executive officers
Conduct, tabulate, and summarize surveys for reviewers prior to their arrival on campus

## Slide 8: Preparation for Review
Development of Steering Committee
  4-7 members representing department
  Select date
  Select reviewers
  Work on charge
  Summarize internal review stats and comments
  Meet regularly from beginning to end – ½ year?
  Coordinate schedules
  Communicate information

## Slide 9: Preparing for the Review – reviewer perspective
Develop a team of reviewers to cover the client’s needs
Determine what the institution is looking for
Develop list of interviews
Receive/review materials provided
Develop a workable schedule
Ask appropriate questions

## Slide 10: The Charge to Reviewers
What do you want the reviewers to know?
What do you want the reviewers to do?
This is what goes into the charge:
  The charge (date, location, length of stay, etc)
  Compensation
  Specific outcomes of the review
  Other things you want them to know
Notes: This is important. What are the politics at the school? Are they looking at outsourcing? Do you have an agenda to share?
Who do you want them to see? President? VP? Provost? Who is it important they see? That they not see?

## Slide 11: Exercise - Outline a Charge
Get in groups of 3 and come up with a charge for your department’s external review. For simplicity, they can be bullet points. Be creative, or at least be entertaining.

## Slide 12: Documentation for Review
Items to send to reviewers
  Mission/Vision/Core Values
  Organization charts
  Strategic plan
  Financial reports
  Annual reports
  Internal review statistics
  Surveys, Executive Summaries
  Publications, contracts, guidebook

## Slide 13: Communication between school and Reviewers
Most communication goes through chair
Chair is the key contact with Client
The Reviewers review materials, etc. and through Chair may request additional info
Reviewers speak regularly before, during and after about observations
Provide documentation a month in advance (desired); mode to be determined

## Slide 14: Site Visit – Reviewer Perspective
At each session explain the review’s purpose
Ask some open ended questions
The reviewers listen and ask for clarification
Absolutely amazing what people will share
Reviewers “touch base” at end of each day to share thoughts

## Slide 15: Site Visit – Institution Perspective
Split the reviewers by “expertise”
Supervisors not in same group as staff
Communicate with staff about their role
Bring in reviewers that provide balance
Staff concerns about review
Expect employees to be mostly honest
Expect reviewers to be honest with client

## Slide 16: Benefit from our experience…
Communicate, communicate, communicate!
Vary schedule times
Attend Standards Institute prior to review
Be specific about what to ask
Meet with senior staff at beginning and end
Be knowledgeable of open records laws
Don’t get defensive when you see the report
Follow up with the recommendations

## Slide 17: The Review Report
The report can take a variety of forms
The first draft is often very rough
Focus is on key themes observed
Client can ask for clarification (and fight for what should/shouldn’t be included)
Additional drafts may be needed.
Don’t pay them until the report is submitted
Notes: You can make some suggestions and edit some wording, but you can’t change their conclusions even if you are paying them.

## Slide 18: Post review followup
Followup must occur to legitimize the review
Report is the tip of the iceberg
Meet as senior staff, discuss and prioritize recommendations – accept or reject
Distribute the report to appropriate entities
Continue to follow up until complete
Notes: Distribution - we sent to every departmental employee electronically

## Slide 19: Questions and Closing Thoughts
External reviews are worth the money
Offer what you can afford; some may do it for minimal money just for the experience
Don’t rush it; good reviews take time
Use the review to improve your operation
Thank you for coming to the program!